## UNICEFF
UNICEF
UNICEF ¦¦ INC3727947 ¦¦ CZ2141064H ¦¦ Re: HPE Support Case 5381305821 for HPE ProLiant DL360 Gen10 Server ref: _00Dd0bUlK._500Kh0WL4c3:ref: Link down on Adapter slot 0 - Sent mail to customer, awaiting update from customer –à Completed INC closed, we can proceed to close the case once asked
UNICEF: CHG0041750-activity from OS end to Install the SUSE Linux Enterprise Server.- Activity in progress.
CTASK0202889- Compute team to assist with Screen share. On 11th April. Wintel team will provide access awaiting update – Linux OS is installed, unable to access server, sakthivel.rajendran@hpe.com is checking with customer and network team –Network down critical alert came, Linux OS informed VLAN and NIC, Gateway settings configuration in progress.They will share the status to the customer, if required we need to log case and confirmation from sarin-kumar.othayoth@hpe.com.
RE: Unicef ¦¦ Host: SPAVSQLDB012-ilo.unicef.org ¦¦ Issue: Server reset ¦¦ RITM0217327
RE: UNICEF ¦¦ Node SPAVSQLDB011 ¦¦ Server reset Detected ¦¦ RITM0217462
RITM0215650- CO21 Adel and BT are working on this-
Onboarding of new server - ITBRSQLDB312 CHG0042355 – Activity in Progress à Once OS team confirms perform SPP upgrades – iso file is getting downloaded we need to get on the call to punch in the credentials.=> wintelgroup downloaded "windows Server 2016" ISO file on the Italy Jump BT from compute co-ordinating the activity.

## MERCK
MERCK:
Merck ¦¦ GreenLake Weekly Stand-Up - 26th March 2024 – File Location : This PC/Local Disk C/Compute
CR’s Approved, Placeholder created
L
· Ctchpntxe12 and Ctchpntxe13 BIOS upgrade is Postponed – We will get update on schedule
· RE: Merck ¦¦ CHG0041323 ¦¦ BIOS Upgrade from version 1.64 to 1.90 ctchpntxe08n02.merck.com in Cluster ctchpntxe08 to complete the BIOS upgrade once the VM:uswsap0553 issue is fixed – awaiting update from customer.
· CHG0041328 - Ctchpntxe10n01.merck.com is pending, HCL Windows and Linux team to check on the issue
Merck ¦¦ Internal ¦¦ Bios Upgrade Pending list – Awaiting update from Rajesh
5381185747 ¦ 2M232100ML ¦ - Unable to communicate with the management processor, alert is triggered from One View – Received analysis to update the controller firmware / ILO reset /OV refresh.- Monitor the host and close the case. – Saturday and Sunday we might receive incs need to monitor
5381253273-We have received the case to check the bios VULNERABILITY- L2 has to come back with the supporting document

## ULTA
ULTA
ULTA Inc. ¦¦ Warranty alerts on 2 devices -Sent mail to MSM – Awaiting update from Sheryl– Contract doesn’t expire until 6/30/24, if we receive any new alert let her know.--> Sheryl submitted SAID to the entitlement team for the contract extension.
INC3698238- The warranty or contract on 1 device are about to expire- looped in ASM and MSM- Please share details: Adel has shared the details, looped in ASM and MSM : Awaiting update.
Re: ULTA ¦¦ INC3698238 ¦¦ The warranty or contract on 1 device are about to expire - Warranty expires on June 30, 2024.

## MLF
MLF:-
MLF: DL, SD Flex, OVA and Synergy Firmware & Software Upgrades—Email from Hubert to plan infra upgrades—Awaiting update from customer to confirm the schedule. Firmware Upgrade on Non-Prod environment Synergy Environment
MLF ¦ CHG0042245 ¦ CR for approval : MLF ¦ Upgrade Prod Synergy Composers 8.80 activity on 20th April.
CR approved – Placeholder created
CHG0042440 - MLF ¦ Shared infrastructure and SSP update on Prod-SAP synergy hosts.-- Approved – Sunday Richa & Adel will perform the update.
CHG0042457- MLF ¦ Upgrade Prod Non-SAP computers to SSP 2024.01.02 + iLO5 3.01 & Upgrade DL380 Gen10 Plus servers to SPP 2023.09.00.04-- Sent for approval - Approved. -Need to create place holder

## FORD
FORD
· FORD ¦ Warranty or contract about to expire: Customer has renewed contract and Account team is working on adding the devices back in contract. Incase support needed, need to follow the trust process, and loop the ADM - Jonathan Dlugi to the email.
· RE: SR ticket request for Ford Motor Company (Dynatrace) ¦¦
request is to increase 6TB +5Gb Disk space -SDM - looped stakeholder and awaiting an update.
· Critical patches needed on ProLiant DL360 series Gen10 – Need to check and prepare action plan.-will work with TAM for spp upgrade to be done.-vikas will work with TAM for spp upgrade – Mail send to TAM with firmware gap analysis. If they request for AHS logs we need to share,
· Host: - e2h2r2021sd1d, e2h1r1086sd2d, Cases: - 5381039490, 5381039768 Since we didn’t receive any alert in OV and in RMC, hence logged sfdc case to investigate
once we get any emails for logs, please take care – case owner ushas.vinod@hpe.com will work.
RE: HPE Support Case 5381039490 ref:_00Dd0bUlK._500KhW9gq7:ref Serial Number, 5UF933B5XM [Refer to 5380418671] The predictive drive failure alert was not visible in OneView or RMC- Break fix team asked for debug logs and OS reports - Debug and OS logs/output are shared the logs – Logs provided Awaiting analysis Follow up – Ushas Vinod will consolidate all the details from ERT and update.- we have received analysis to upgrade the DCD to version but Ushas mentioned she will check internally and let us know the plan of action
CHG0042428 ¦¦ FORD ¦¦ Server Reboot – activity was completed and was already approved by Prabhu.
The CR was created for documentation purpose.- vinod will proceed with closure.

## LYB
LYB
Alert124052474 ¦¦ The warranty or contract on 18 devices are about to expire. Oneview Severity = Warning Alert State = Active Alert modified time is 2024-03-03T10:30:00.181Z – Mail sent to ASM – Awaiting update
RE: LYB ¦¦ Warranty ex : Brad informed, we can proceed to log case normally as the servers are in warranty till May 2024
LYB ¦¦ CHG0039870 ¦¦ Physical Server Decommission - CR created and assigned to ITAM team for the same.. – Awaiting Update–Need to work with ITAM team
· RMC lab mode disable with ERT Marc Moin ask Nithesh to look into this. – this was requested by Sreenivas from storage team – Informed Nithesh—Nithesh checked with Thyagu and Sreenivas, they checked with ERT on Slack – ERT will update Thyagu & Sreenivas if a case is needed or not to carry on.-- Tentative date month of April
· Lyondell Bassell ¦ INC3596244 ¦ WARNING: Used disk space was 80.70 % (Used: 825.70 GiB, Free: 198.04 --> Need to clear the space.
· If any P3/P4 INC’s received, please ping some from “LYBHPEGMS” team.
· Assignment group : pod1_dcaas_ams@hpe.com
· LYB ¦¦ INC3733547 ¦¦ 5381334442 ¦¦ CHG0042242¦¦ DIMM failure.
P1 case – 5381335887 / INC3734803 -- We got analysis that there is no hardware issue .
· RE: <CASE:5381335887>Lyondellbasell Industries/US/SDF/Services running slow, backups failing [ ref:_00Dd0bUlK._500Kh0VTMyg:ref ] –host EDCHDF03
· Checking with Palani if ERT is required
· INC3737632¦¦Smart Hands Request for the Lyondell/HPE Cage ¦ ADC-B7-RU35 ¦--- Network team,storage team amd MSM worked on a bridge call and requested COLO PM team to send engineer onsite to reseat the cable.—FLM Issue got resolved.
· Re: LYB ¦¦ HPE Support case 5381336019 logged for Intermittent Performance issue ¦ ref:_00Dd0bUlK._500Kh0WAN2o:ref—Yet to share the logs awaiting update from breakfix team to know what logs are required –( replica of case 5381335887) – host EDCHDF03
· LYB - Nimble Volume Extension through OneView – checked today and we can expand the existing volume and updated same to Thyagu over chat.
·
· CHG0042323 - LYB ¦¦ Adding the missing Prod Networks to the LE05 as part of the Synergy Environment Housekeeping task – Activity is on 2024-04-23 13:30:00 IST, sent for approval.
· RE: Maintenance on HPC nodes/Splunk – Upgrade of Bright Clustger Manager and the OS in progress from 7.30 PM IST till tomorrow – Need to validate
LYB ¦¦ SD-Flex time sync issue
SFDC case-5381401773 logged and internal email sent with findings
as per BF team, we need to setup NTP..
below are the commands..(we need to check FQDN IP)
show ntp
set ntp server=FQDN of NTP
reboot rmc
·
· -we dont need downtime for this activity
Raise 3 CRs as per Naveen’s email (Linux) and keep it in draft state for tomorrow’s meeting
CHG0042482 | NTP Configuration on Prod Servers
CHG0042483 | NTP Configuration on Non-Prod Servers
CHG0042484 | NTP Configuration on HA/DR Servers
CR sent for approval
RE: LYB ¦ INC3747982 ¦ 5381405146 ¦ Remote Support Ticket: A fibre channel HBA port has changed to a state of link down ¦ Host edchdd03 –as per Storage team, SFP has to be replaced from ourside first and they told we will discuss in pre war call today as we proceed with same sfdc case then SL will miss..
We are waiting for CE details and also we need to create CR to perform SFP replacement.

## BIOGEN
BIOGEN
HPE Support Case 5380667098 | for HPE Superdome Flex 280 Base System ref:_00Dd0bUlK._500Kh0VyIsF:ref¦ INC3526492-RMC is not reachable but its pingable-.- we need to send CE to check RMC Biogen --> 10:30 am IST - 30th March --> CHG0041100 external NCR sent for approval
S/N 5UF238K24L ¦ SD flex 280 CE is available this week Tuesday 26Mar and Thursday 28 Mar. this needs to be checked in the CAB meeting on Monday.---Awaiting update from ASM - if any CE will be assigned on 30th
CHG0041100 : abandoned for now, activity is postponed until 1st week of April due to CE unavailability.
New CR will be created, once we get the schedule – Schedule on 12th April 5:30 PM EST, awaiting CE details.- Followed up – Received CE details , site access request raised - CHG0042004 pushed for approval activity @ 3am IST 13th April.- We would need to arrange new ERMC cable. As we were unable to connect with the one we have. once part ETA received- onsite need to be rescheduled.
New Work Order created: 00703492 on case 5380667098 and part is recommended.
Follow up with Bobbie as the correct part needs to be ordered.
New ECR - ECR#CHG0042157 Place holder created – Awaiting part order status and ETA. - part has been delivered same informed to Bobbie – Check with Thahir if we can schedule the activity.

## ADI
ADI
INC3547179 - Leaf certificate with alias name ad.analog.com_10.65.72.110 is about to expire on 2024-05-16 –Nithesh has sent email to ADIColoSynergy team to Requesting assistance in renewing the certificate and also to update the same in OneView as it required local admin rights.— Customer told they will update the certificate by mid of April
Re: Alert from Security - Leaf certificate with alias name ad.analog.com_10.64.51.11.
CHG0041694- ¦ SSP update to version 2024.01.02 Activity 2024-04-10 17:30:00 IST - CR Approved - Placeholder created - SSP file is uploaded to the OV – Today we have activity at 5:30PM
5381290045 -- Logged case and working on this – Check with Nithesh and take updates
3035 card - LPFC driver has to be downgraded on the Latest ESXI. Nitesh working with ERT team, Testing will be done.

## PWC
PWC:
INC3733347 / INC3733345
RE: HPE Case ID: 5381329071 / 5381329319/5381205046 - Follow up with the onsite coordination team. to get an update on the DIMM ordered and also to assign this onsite task to Abe Hollingsworth. Relocation of 4 servers completed. DIMM replaced on 001 and 002.
After the second restart the 003 and 004 had RMC communication issue. After restarting individually the RMC connected back. No issue with the server.

## DISNEY
DISNEY
Whoever had an access issue and it is not working contact - suyog-sandesh.nashte@hpe.com
5381429443/ INCTASK0013314 -- > Logged a case as requested by Vmware team àLogs shared, please take it from there Re: Disney ¦¦ HPE Support Case 5381429443- need to share the screenshot with vmware- INC3752651
Snips has been provided and looped VMware team to respond for the POA suggested.

## ABBVIE
ABBVIE :
We received multiple alerts for AbbVie : A service event has been generated against npar 0 for reason ID 1383.
Alerts got auto resolved on OV, however case was raised for analysis, we have to upload the requested logs---IDC logs to be uploaded. (have informed Kumaran about the same).
RE: HPE Support Case 5380951337 for HPE Superdome Flex Server. INC3653247—WE have to check with OS and network team -- Hpcaas – show case list uploaded, looped HPCass team to share OS log….awaiting analysis. à Awaiting for SOS report. Awaiting update from Break fix team. Follow up with the OS team for correct logs.
Need to share show cae commands.—currently OS breakfix is working with HP-CAAS team
INC3742822 ¦¦ A service event has been generated against npar 0 for reason ID 1383 ¦ 5UF048FBR3 ¦ SD flex
INCTASK0013268 – assigned to HP-CAAS team for screenshare-- host is healthy, we sent an email support team about the alert
abbvie : Internal ¦¦ Abbvie ¦¦ SDFlex ¦¦ Firmware update POA needed –
8th may is the maintenance window need to plan for Firmware upgrade – Requested TAM to share analysis

## DYNALIFE
DYNALIFE
Dynalife ¦¦ SCTASK0118568 ¦¦ SCTASK0118567 ¦¦ SCTASK0118569 ¦¦ Lifecycle/Patch Management of HPE DL380 Gen10+ 8SFF NC CTO Svr Awaiting update from MSM and ASM

## Suncor
Suncor:
Suncor ¦¦ Add vLAN 500 for Suncor's internal change ¦¦ CTASK0204367 ¦¦CHG0042161—vlan added - customer to confirm the closure
Suncor ¦ BIOS and SPS Security Vulnerability ¦ CHG0042290 ¦ 22nd April ¦ - Sent for approval

## W.R.Grace
W.R.Grace - CHG0042224 - ESXi Patching on sapnonprd cluster nodes.
CTASK0204690 - Perform the ESXi host validation with respect to hardware - On 19thth April 6:30 pm to 20th April 2:00 am – After Esxi upgrade, push the drivers as well if required
CHG0042362- SSP update on bwoh and 505 cluster hosts to 2024.01.02 – Activity on 2024-04-22 18:30:00 IST,
Sent for approval, Richa will create placeholder.

## Mitsubishi
Mitsubishi
CHG0042218 for MHIA Compute Cluster Upgrade ¦¦ PROD ¦¦ PROD_Cluster01 - SPP and VMware OS Upgrade. : 2024-04-20 . @ 4.30pm IST
CTASK0204706 - Update will be carried out by GRS Lifecycle team, we have to collaborate when needed. - We will have to be Present Just in case.
MHIA Compute Cluster Upgrade ¦¦ PROD ¦¦ PROD_Cluster01
CTASK0205859 ¦¦ CHG0042218
2024-04-20 16:30

## Deloitte
Deloitte
- 5381329112 / MXQ936040L / INC3730840 - part (Synergy 3820C 10/20Gbe 2-port mezzanine controller) has been ordered. Part will be delivered onsite on 15th April as informed by dispatch team on call when followed up. Also CE details have been shared- dispatch team has sent the site access to the customer- Awaiting update.
FW: HPE Support Case 5381329112-531: Site Access needed for Service Engineer ¦ DO NOT EDIT THIS LINE<CASE: 5381329112 > ¦ 559255 [ ref:!00Dd00bUlK.!500Kh0WAJhS:ref ]
Service Window Apr 15, 2024 08:00-Apr 15, 2024 17:00(Time zone: Eastern Daylight Time ).
RE: Deloitte ¦¦ INC3730840 ¦¦ USNDCESX2001 ¦¦ Host controller has a new status of not Connected--mail sent to customer to check if issue is resolved post part replacement
HPE Support Case 5381328996 for HPE Synergy 480 Gen10 Compute Module ref:_00Dd0bUlK._500Kh0TbZW2:ref- CHG0042252 ECR created and pushed for approval : Please Follow up for Approval : Activity tomorrow 15th April @5.30 pm IST—customer has been looped on CE details email – Activity Completed- Awaiting for Host status from customer’s End